## Customer
Project Name | Functional Testing Using Selenium Web Driver | https://phptravels.net/login
Module Name | Customer
Created By | Sneha N
Created Date | 2022-02-14
Reviewed by
Reviewed date
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_02/03/04 | DEF_CS_01 | Customer shouldn't able to login and "Wrong credentials try again!" warning message should be displayed | Invalid credentials are not working. | Open the website https://phptravels.net/login Enter invalid Email ID and valid password Click Login button | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_06 | DEF_CS_02 | Application should redirect to Add Funds page | Its not directing to the page. | Open the website https://phptravels.net/login Login to application as customer Click Add Funds Link | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_07 | DEF_CS_03 | Application should redirect to My Profile page | Its not directing to the page. | Open the website https://phptravels.net/login Login to application as customer Click My Profile Link | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_08 | DEF_CS_04 | Customer should be able to logout from the page and application should redirects to login page | Its not directing to the page. | Open the website https://phptravels.net/login Login to application as customer Click logout Link | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_09 | DEF_CS_05 | Application should redirects to payment page | Its not directing to the page.Click on pay is not working. | Open the website https://phptravels.net/login Login to application as customer Click Add Funds Link Check on pay with paypal radio button Click on pay now | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_11 | DEF_CS_06 | Customer should be able to update address and profile updated successful message should be displayed | No such updations are working | Open the website https://phptravels.net/login Login to application as customer Click My Profile Link Click on View Voucher Update address Click on update profile | Major | HIGH | New

## Agent
Project Name | Functional Testing Using Selenium Web Driver | https://phptravels.net/api/admin
Module Name | Agent
Created By | Sneha N
Created Date | 2022-02-14
Reviewed by
Reviewed date
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_O2/03/04 | DEF_AG_01 | Customer shouldn't able to login and "Wrong credentials try again!" warning message should be displayed | Invalid credentials are not working. | Open the website https://phptravels.net/login Enter invalid Email ID and valid password Click Login button | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_07 | DEF_AG_02 | Application should redirect to My Profile page | Its not directing to the page | Open the website https://phptravels.net/login Login to application as Agent Click My Profile Link | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_17 | DEF_AG_03 | Agent should be able to update Amount USD to INR for the account and after updation results should display amount in INR | Dropping down from USD but updation is not working | Open the website https://phptravels.net/login Login to application as Agent Select INR from dropdown list | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_16 | DEF_AG_04 | Agent should be able to search hotel by city name | Not able to search by city name | Open the website https://phptravels.net/login Login to application as Agent Click Hotel Link Enter Valid city name Select Valid Check in date Select Valid Check out date select travellers details from dropdown click Search button | Major | HIGH | New

## admin
Project Name | Functional Testing Using Selenium Web Driver | https://phptravels.net/login
Module Name | Agent
Created By | Sneha N
Created Date | 2022-02-14
Reviewed by
Reviewed date
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_02/03/04 | DEF_AD_01 | Customer shouldn't able to login and "Wrong credentials try again!" warning message should be displayed | Invalid credentials are not working. | Open the website https://phptravels.net/login Enter invalid Email ID and valid password Click Login button | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_06 | DEF_AD_02 | Admin should be able to delete a record whose booking status is cancelled | Not able to delete the records | Open the website https://phptravels.net/api/admin Login to application as Admin Click My Booking Link Click on cancelled bookings Click on cross mark click ok for validation message | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_07 | DEF_AD_03 | Admin should be able to update booking status from pending to confirmed and count gets automatically updated into the dashboard | No such updations are working | Open the website https://phptravels.net/api/admin Login to application as Admin Click My Booking Link Click on pending bookings Select a customer and update booking status from pending to confirmed Check if the count gets updated automatically in dashboard | Major | HIGH | New

## Supplier
Project Name | Functional Testing Using Selenium Web Driver | https://phptravels.net/api/supplier
Module Name | Supplier
Created By | Sneha N
Created Date | 2022-02-14
Reviewed by
Reviewed date
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TC_02/03/04 | DEF_SP_01 | Customer shouldn't able to login and "Wrong credentials try again!" warning message should be displayed | Invalid credentials are not working. | Open the website https://phptravels.net/login Enter invalid Email ID and valid password Click Login button | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_08 | DEF_SP_02 | Should able to redirect to flight page | No such option is visible in the Dasborad | Open the website https://phptravels.net/api/supplier Login to application as Supplier Click Flights Link | Major | HIGH | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_09 | DEF_SP_03 | Should able to redirect to visa page | No such option is visible in the Dasborad | Open the website https://phptravels.net/api/supplier Login to application as Supplier Click Visa Link | Major | HIGH | New